## New Tasks
[8 empty] | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16
WBS | Tasks/Activities | Responsible | Start | Finish |  | % Tamamlanma | Work Days | P | S | C | P | C | P | S | C | P | C | P | S | C | P | C | P | S | C | P | C | P | S | C | P | C | P | S | C | P | C | P | S | C | P | C | P | S | C | P | C
2.0 | Testing & Quality Assurance | Mahmut & Eren | 30.03.2026 | 13.04.2026 | 11 | 0% | 11
2.1 | Unit Tests | Mahmut Muhammed Pakim | 30.03.2026 | 02.04.2026 | 4 | 0% | 4
2.2 | Integration Tests | Mahmut & Eren | 03.04.2026 | 08.04.2026 | 4 | 0% | 4
2.3 | User Acceptance Testing (UAT) | Eren Görkem Çolak | 09.04.2026 | 13.04.2026 | 3 | 0% | 3
3.0 | Improvements & Updates | Mahmut & Eren | 14.04.2026 | 01.05.2026 | 14 | 0% | 14
3.1 | Security Improvements | Mahmut Muhammed Pakim | 14.04.2026 | 16.04.2026 | 3 | 0% | 3
3.2 | Performance Optimization | Eren Görkem Çolak | 17.04.2026 | 21.04.2026 | 3 | 0% | 3
3.3 | Bug Fixes | Mahmut & Eren | 22.04.2026 | 24.04.2026 | 3 | 0% | 3
3.4 | UI/UX Updates | Eren Görkem Çolak | 27.04.2026 | 29.04.2026 | 3 | 0% | 3
3.5 | New Feature Additions | Mahmut Muhammed Pakim | 30.04.2026 | 01.05.2026 | 2 | 0% | 2
4.0 | Documentation | Mahmut & Eren | 04.05.2026 | 13.05.2026 | 8 | 0% | 8
4.1 | Technical Documentation | Mahmut Muhammed Pakim | 04.05.2026 | 06.05.2026 | 3 | 0% | 3
4.2 | User Guide | Eren Görkem Çolak | 07.05.2026 | 08.05.2026 | 2 | 0% | 2
4.3 | Project Report | Mahmut & Eren | 11.05.2026 | 13.05.2026 | 3 | 0% | 3
5.0 | Final Delivery & Presentation | Mahmut & Eren | 14.05.2026 | 20.05.2026 | 5 | 0% | 5
5.1 | Final Presentation Preparation | Mahmut & Eren | 14.05.2026 | 18.05.2026 | 3 | 0% | 3
5.2 | Project Submission | Mahmut & Eren | 19.05.2026 | 20.05.2026 | 2 | 0% | 2