## WBS
WBS Code | Level | Deliverable / Work Package Name | Description | Responsible Person / Team | Acceptance Criteria | Estimated Duration (days) | Estimated Cost ($) | Dependencies | Notes
1.0 | 1 | Eventix Ticketing Platform | Complete event e-commerce system | Mahmut & Eren | All deliverables accepted | 30 | 1500 | - | Student Project
1.1 | 2 | User Management System | Registration, login, user profiles | Mahmut & Eren | Auth system works smoothly | 5 | 200 | - | Student Project
1.1.1 | 3 | Registration & Login Backend | JWT auth, registration, validation | Mahmut Muhammed Pakim | Users can securely log in | 3 | 100 | - | Student Project
1.1.2 | 3 | Profile & Roles UI | Frontend forms, profile updates | Eren Görkem Çolak | Profiles update successfully | 2 | 100 | 1.1.1 | Student Project
1.2 | 2 | Event Catalog System | Event listing, categories, structure | Mahmut & Eren | Events load without errors | 7 | 350 | - | Student Project
1.2.1 | 3 | Event CRUD & Database | SQLite DB schema, CRUD endpoints | Mahmut Muhammed Pakim | Backend API runs properly | 3 | 150 | - | Student Project
1.2.2 | 3 | Frontend Listing & Details Page | Event cards, search, event details UI | Eren Görkem Çolak | Responsive UI displays events | 4 | 200 | 1.2.1 | Student Project
1.3 | 2 | Payment & Ticketing Flow | Checkout, virtual POS, seating | Mahmut & Eren | Tickets can be purchased | 6 | 400 | 1.2 | Student Project
1.3.1 | 3 | Payment & Checkout Logic | Virtual POS simulation, promo codes | Mahmut Muhammed Pakim | Payments process accurately | 3 | 200 | 1.1.1 | Student Project
1.3.2 | 3 | QR Generation & Seat Selection | Seat plan UI, QR code ticket creation | Eren Görkem Çolak | Seat map works, QR generated | 3 | 200 | 1.2.1 | Student Project
1.4 | 2 | Reporting & Dashboards | Admin and Organizer panels | Mahmut & Eren | Management panels load | 7 | 350 | 1.2 | Student Project
1.4.1 | 3 | Organizer Rev & Analytics | Gross/Net revenue calculation logic | Mahmut Muhammed Pakim | Correct commission/revenue output | 4 | 200 | 1.3 | Student Project
1.4.2 | 3 | Admin Event Approval UI | Admin user/event lists, approve/reject | Eren Görkem Çolak | Admin can approve/reject events | 3 | 150 | 1.2.1 | Student Project
1.5 | 2 | Platform Operations | Emails, notifications, and UI finish | Mahmut & Eren | System alerts trigger correctly | 5 | 200 | - | Student Project
1.5.1 | 3 | Email Service & Notifications | SMTP mailer, password resets | Mahmut Muhammed Pakim | Emails are sent on triggers | 3 | 100 | - | Student Project
1.5.2 | 3 | UI/UX Polish & Mobile CSS | Overall glassmorphism, responsive UI | Eren Görkem Çolak | No visual bugs on mobile | 2 | 100 | - | Student Project
2.0 | 1 | Test & Kalite Güvence | Tüm sistemin test edilmesi ve hata giderme | Mahmut & Eren | Tüm testler başarılı | 10 | 400 | 1.0 | Student Project
2.1 | 2 | Birim Testleri (Unit Tests) | Backend API endpoint'leri için birim testleri | Mahmut Muhammed Pakim | Tüm endpoint'ler test edilmiş | 4 | 150 | 1.0 | Student Project
2.2 | 2 | Entegrasyon Testleri | Modüller arası entegrasyon testleri (ödeme-bilet-email akışı) | Mahmut & Eren | End-to-end akışlar sorunsuz çalışıyor | 3 | 150 | 2.1 | Student Project
2.3 | 2 | Kullanıcı Kabul Testleri (UAT) | Gerçek kullanıcılar ile test senaryolarının yürütülmesi | Eren Görkem Çolak | Kullanıcı geri bildirimleri olumlu | 3 | 100 | 2.2 | Student Project
3.0 | 1 | İyileştirme & Güncelleme | Güvenlik, performans ve yeni özellik güncellemeleri | Mahmut & Eren | Tüm iyileştirmeler uygulanmış | 12 | 500 | 1.0 | Student Project
3.1 | 2 | Güvenlik İyileştirmeleri | SQL injection, XSS, CSRF korumaları, input validasyon | Mahmut Muhammed Pakim | Bilinen güvenlik açıkları kapatılmış | 3 | 100 | 1.0 | Student Project
3.2 | 2 | Performans Optimizasyonu | Veritabanı sorgu optimizasyonu, caching, sayfa yükleme hızı | Eren Görkem Çolak | Sayfa yükleme süresi < 3 saniye | 2 | 100 | 1.0 | Student Project
3.3 | 2 | Hata Düzeltmeleri (Bug Fixes) | Test aşamasında tespit edilen hataların giderilmesi | Mahmut & Eren | Bilinen tüm buglar çözülmüş | 2 | 100 | 2.0 | Student Project
3.4 | 2 | Kullanıcı Arayüzü Güncellemeleri | Kullanıcı geri bildirimlerine göre UI/UX iyileştirmeleri | Eren Görkem Çolak | Güncellenmiş UI kullanıcı onayı almış | 3 | 100 | 2.3 | Student Project
3.5 | 2 | Yeni Özellik Eklemeleri | Wishlist, gelişmiş filtreleme, bildirim tercihleri | Mahmut Muhammed Pakim | Yeni özellikler sorunsuz çalışıyor | 2 | 100 | 1.0 | Student Project
4.0 | 1 | Dokümantasyon | Proje teknik ve kullanıcı dokümantasyonu | Mahmut & Eren | Dokümantasyon eksiksiz teslim edilmiş | 7 | 250 | 1.0 | Student Project
4.1 | 2 | Teknik Dokümantasyon | API dokümantasyonu, veritabanı şeması, mimari diyagramlar | Mahmut Muhammed Pakim | API endpointleri ve DB şeması belgelenmiş | 3 | 100 | 1.0 | Student Project
4.2 | 2 | Kullanıcı Kılavuzu | Son kullanıcı için platform kullanım rehberi | Eren Görkem Çolak | Tüm kullanıcı rolleri için kılavuz hazır | 2 | 75 | 1.0 | Student Project
4.3 | 2 | Proje Raporu | Final proje raporu, metodoloji ve bulgular | Mahmut & Eren | Rapor akademik standartlara uygun | 2 | 75 | 4.1, 4.2 | Student Project
5.0 | 1 | Final Teslim & Sunum | Projenin son teslimi ve sunum hazırlığı | Mahmut & Eren | Proje başarıyla teslim edilmiş | 5 | 100 | 2.0, 3.0, 4.0 | Student Project
5.1 | 2 | Final Sunum Hazırlığı | Demo senaryosu, sunum slaytları, canlı demo hazırlığı | Mahmut & Eren | Sunum materyalleri hazır | 3 | 50 | 5.0 | Student Project
5.2 | 2 | Proje Teslimi | Kaynak kod, dokümantasyon ve raporun final teslimi | Mahmut & Eren | Tüm çıktılar teslim edilmiş | 2 | 50 | 5.1 | Student Project